## Improvements
From operational tests | Count of # | Notes
Improve Layout and UI | 19
Contextual help | 14 | With examples and format
Add Locode search in fields and display name with locode | 9 | With option "unknown" when relevant
Generalise file upload and use XLS | 5 | With possibility to download XLS template
Add data controls in forms | 4
DPG database | 4 | Not in scope of project
Allow notification consult and updates from different users, based on agency | 4 | Remove control based on ship company
Improve update of table rows with full deletion | 4
Differentiate Arrival and Departure formalities | 4 | NSW Admin to select arrival and departure formalities
Improve “my ship notification” user interface logic | 3
Improve Date field | 2
Consult and print notifications and confirmation screen | 2
Remove "voyage number" from UI | 2
Display validation screen before submit | 2
Cancel a call | 1 | Only possible if no ATA is recorded
Reject change of ship IMO number in update notification | 1
Propose unified crew & passenger list (for upload, with unified number) | 1
Add possibility to record draft notification | 1
Check if IMO number already exist while creating ship | 1
Improve re-use | 1
Do no update notification type | 1 | Only allowed in initial notification
Grand Total | 85
From Workshop meeting |  | Notes
Support national languages in addition to English (and character sets) |  | MS to provide labels and texts
Link ship data providers to Agencies rather than to Companies
Dynamic updates of locodes from SSN Central (with specific locodes)
Dynamic updates of shipping companies from reference source |  | Source to be investigated
Re-use CSO details from Ship Table when recording a new notification
Add possibility to delete a user accounts, and to filter non enabled users in list
Use digital signature to adress liability issues
Communicate acknowledgments to ship data providers by email |  | In addition to XML and GUI
Display additional information from SSN regarding the ship (refusal of access) to the authorities.
Add feature for text messages to the Ship Data Providers and authorities recorded by the NSW administrator in the homepage

## Test report
# | Description of issue Please describe here the issue (what went wrong or what is missing) | Severity of issue | Functionality where issue was found | MS | Type of change | Suggested change
1 | A notification submitted cannot be be seen/updated/reused by another colleague, in same Agency, who login system with different username/password; probably a field named "agency" should be added to the user profile in order to allow agents working for the same agency to work at the same notifications. | Blocking | Overall functionality | IT | Functionality | Allow notification consult and updates from different users, based on agency
2 | Strongly recommended to avoid any strictly association between Company and Agents; better leaving the freedom to the Agents to choose a Company from a worldwide list / data base (same as ships) or add a new one in case of necessity. This also because same Company could be served by different Agents also in the same port. | Blocking | Overall functionality | IT | Functionality | Allow notification consult and updates from different users, based on agency
3 | Every company user can update other companie's notifications | Major | Overall functionality |  | Functionality | Allow notification consult and updates from different users, based on agency
4 | The issue describes the way of representation of the already entered data - Data Provider accounts to be able to see only the request notifications, already created by their account only | Minor | Overall functionality |  | Functionality | Allow notification consult and updates from different users, based on agency
5 | ONCE SUBIMITTED THE NOTIFICATION THE SISTEM SHOW WHAT HAS BEEN INSERTED, BUT ONCE GO BACK TO MAIN MENU, THERE IS NOT A FUNCTION THAT PERMIT TO READ ONLY THE NOTIFICATION AND PRINT. | Minor | Overall functionality | IT | Functionality | Consult and print notifications and confirmation screen
6 | No Print function |  | Overall functionality | MT | Functionality | Consult and print notifications and confirmation screen
7 | ''Help'' functionality aside input data fields is missing. | Minor | Overall functionality | IT | User interface | Contextual help
8 | Hovering onto the word “i” showing necessary information may be beneficial |  | Overall functionality | MT | User interface | Contextual help
9 | Place a tool-tip with definition and format information to each field |  | Overall functionality | WS1 | User interface | Contextual help
10 | Data fields "DATE" should provide the fast scrolling of the years; differently it is better put by hand. | Minor | Overall functionality | IT | User interface | Improve Date field
11 | In date tools, clicking on the icon should also show the calendar | Minor | Overall functionality | EMSA | User interface | Improve Date field
12 | "draft" version of data entry should be provided; there should be the possibility, for user, to fill different tabs and store data for next updating, without submitting them to the authority. | Major | Overall functionality | IT | Functionality | Add possibility to record draft notification
13 | Previous Port of Call, Store List, Waste declaration: file uploading function should be provided | Minor | Overall functionality | IT | Functionality | Generalise file upload and use XLS
14 | No possibility for dpg or crew list details upload for any type of file | Blocking | Overall functionality | GR | Functionality | Generalise file upload and use XLS
15 | My ships notification shows a large search result when searching for nothing. If you choose a random ship, no notification will show up. Search should only show relevant ships. | Minor | Overall functionality | NO | User interface | Improve “my ship notification” user interface logic
16 | BUTTON MY SHIPS NOTIFICATIONS: NOT WORKING | MAJOR | Overall functionality | GR | User interface | Improve “my ship notification” user interface logic
17 | Buttons "add new notification" and "my ships notifications" appear to have the same functionality. | Major | Overall functionality | GR | User interface | Improve “my ship notification” user interface logic
18 | Clarify the difference between ''add a row'' and ''add new item'' | Minor | Overall functionality | IT | User interface | Improve Layout and UI
19 | Username/Password Fonts do not fit in the box provided |  | Overall functionality | MT | User interface | Improve Layout and UI
20 | In my opinion all the pages in the NSW page should be smaller so as to fit the screen, rather than having to scroll up and down continuously. The standard screen size used by Transport Malta is 17” (4:3). Apart from this some of the fonts used do not fit in the boxes provided in the prototype, making it impossible to read clearly. Mostly since they are not centered horizontally. By reducing the fonts all-round, the user can then zoom in using the browser’s functionality. |  | Overall functionality | MT | User interface | Improve Layout and UI
21 | In tables, when there is only one action button per row, clicking on the row should launch the action (rather than only when clicking on the action icon) | Minor | Overall functionality | EMSA | User interface | Improve Layout and UI
22 | When scaling window the GUI elements are not anchored. Try to rescale the browser window. There is no minimum size defined, no horrisontal scrolling will be added to the browser window. | Minor | Overall functionality | NO | User interface | Improve Layout and UI
23 | Using the latest version of google chrome doesn't solve totally the appearance issue, especially in the login screen. Letters are not aligned correctly in the text fields. | Major | Overall functionality | GR | User interface | Improve Layout and UI
24 | DPG --> Port of loading and discharge; the locode should be automatically retrived from a list after writing the name of the port. This problem concerns every data field where UNLOCODE must be provided. | Minor | Overall functionality | IT | User interface | Add Locode search in fields and display name with locode
25 | Suggested that full name of Port may be entered wherein the system automatically converts it to LOCODE. |  | Overall functionality | MT | User interface | Add Locode search in fields and display name with locode
26 | All locodes should appear with location name "Lisboa (PTLIS)" | Minor | Overall functionality | EMSA | User interface | Add Locode search in fields and display name with locode
27 | while typing in the LOCODES field, it would be very useful to be provided a list with the suggested values for the field | Major | Overall functionality | GR | User interface | Add Locode search in fields and display name with locode
28 | system could use auto complete functionality in many fields (eg search fields, locodes, ports, etc) | Major | Overall functionality | GR | User interface | Add Locode search in fields and display name with locode
29 | Error messages are sometimes a bit technical :) dpg.cargoManifest.cargoManifestContactDetails.fax : Fax Number jepp contains characters. dpg.cargoManifest.cargoManifestContactDetails.email : epostenmin is not valid Email address. numberOfCrew : Number of crew = Crew.Number (list of crew) : Invalid vessel call message. | Minor | Overall functionality | NO | User interface | Add data controls in forms
30 | Should be able to specify Location Source; UNLocode or National/Specific code. | Minor | Manage locations | NO | ? | -
31 | The format for Lat and Long must be clearly specified | Minor | Manage locations | RO | User interface | Contextual help
32 | when creating a new ship and entering its shipping company, CSO field is not automatically filled | Major | Manage ships | GR | Functionality | ?
33 | when creating a new ship, if it already exists, a warning message could appear at an early stage | Major | Manage ships | GR | User interface | Check if IMO number already exist while creating ship
34 | WE SEARCH FOR THE CRUISE VESSEL MSC PREZIOSA BUT A REPLY COME THAT 'VESSEL NOT FOUND'. IT COULD BE AN OUTDATED DATA BASE OF VESSELS AS THE VESSEL TRADING DEFINTELLY 'HIT' THE WATER BACK IN MAY 2013. | MAJOR | Search ships | GR | - | -
35 | When a port of call is inserted at the Ship Identification, this should be auto-completed in the next tabs (e.g. Port Information tab) | Major | Search ships | GR | ? | -
36 | It would be helpful if the error is specified in which tab it is found |  | Create a new notification | MT | ? | -
37 | After you click submit to view the notification only the number is visible. Having a ship type with just a number is not user-friendly |  | Create a new notification | MT | User interface | Improve Layout and UI
38 | Bold fonts for titles and boxes will be better for reading the notification |  | Create a new notification | MT | User interface | Improve Layout and UI
39 | In tab title, link should be on icon in addition to text | Minor | Create a new notification | EMSA | User interface | Improve Layout and UI
40 | Add the ship’s type in the header section in each tab | Minor | Create a new notification | WS1 | User interface | Improve Layout and UI
41 | Submit summary, lists everything even if the parts are empty. The system should give an easy summery with only rellevant parts. | Minor | Create a new notification | NO | User interface | Improve Layout and UI
42 | "Update" and "Continue". What is the main difference between both? |  | Create a new notification | MT | User interface | Improve Layout and UI
43 | The contrast of the colors used in textbox borders has low contrast. The hoover functionality (gray shaddow effect) does not work if you type the form with only a keyboard input (tab to next feeld). | Minor | Create a new notification | NO | User interface | Improve Layout and UI
44 | There is no immediate check of accuracy of data that inserted until the user press the submit button | Minor | Create a new notification | GR | User interface | Add data controls in forms
45 | It is not clear what should be inserted in the field voyage number when doing a new notification | Minor | Create a new notification | GR | Functionality | Remove "voyage number" from UI
46 | The user should be able to read the summary before submitting the final results. | Minor | Create a new notification | NO | Functionality | Display validation screen before submit
47 | After pressing the submit button for a notification, a confirmation or a total review should be displayed before the final submission of data | Major | Create a new notification | GR | Functionality | Display validation screen before submit
48 | FOR CRUISE VESSELS : IN VIEW THAT THESE VESSELS CALL DAILY IN REPEATED PORTS OF CALL, IT COULD BE AN OPPORTUNITY TO AVOID ANY DOUBLE ENTRY AND KEEP THE INFORMATION REQUIRED TO THE MINIMUM MANUAL INPUT. |  | Create a new notification | GR | Data
49 | Check funtionality of ''SUBMIT'': if click at the end of each function we must go back to main menu and select again ''my notification''.It should be useful to remain in the same notification even after the submission for each tab. Moreover if you click on ''Next Step'' there is a risk of loosing all data entered if something happens in the meantime. | Minor | Update an existing notification (button “update”) | IT | User interface | -
50 | It should be possible to cancel a call | Major | Update an existing notification (button “update”) | EMSA | Functionality | Cancel a call
51 | User should not be allow to change the notification type (Arrival/Departure) when updating a notification | Major | Update an existing notification (button “update”) | EMSA | Functionality | Do no update notification type
52 | "Departure: WASTE / SECURITY / HEALT from arrival should not be reused, since these are communicated in prearrival only. Differently there should be the possibility to cancel more easily at once the entire notification reused. | Major | Re-use of arrival to create a departure notification (button “continue”) | IT | Functionality | Differentiate Arrival and Departure formalities
53 | on departure the data "ETA TO PORT OF CALL" and "ETA TO NEXT PORT" don't appear when using the function "continue" | Major | Re-use of arrival to create a departure notification (button “continue”) | IT | Functionality | Differentiate Arrival and Departure formalities
54 | Include configuration of data groups to be used for arrival notifications, and data groups for departure notifications. This is to be applied to Web interface and System interface (if unecessary data is received, then ignored) | Major | Re-use of arrival to create a departure notification (button “continue”) | EMSA | Functionality | Differentiate Arrival and Departure formalities
55 | Departure notification : it is necessary to cancel one by one IMO containers / or other DPG already discharged at PORT OF CALL otherwise will appear also on departure notification.DPG reuse, in this sense, is not suggested.Differently we support and addictional functionality by which it is possible to cancel group of items more easily. | Major | Re-use of arrival to create a departure notification (button “continue”) | IT | Functionality | Improve update of table rows with full deletion
56 | Departure notification : it is necessary to cancel one by one the PASSENGERS OR CREW ( important for passenger vessels) / desembarked at PORT OF CALL otherwise will appear also on departure notification. Upsetting | Major | Re-use of arrival to create a departure notification (button “continue”) | IT | Functionality | Improve update of table rows with full deletion
57 | When pressing Continue on a previous voyage it does not fill the data from the previous voyage in the correct fields. "Next port" from the previous voyage should be in the "Port of Call field", "Port of Call" from the previous voyage should be in the "Last port" field. | Minor | Re-use of arrival to create a departure notification (button “continue”) | NO | Functionality | Improve re-use
58 | BUTTON RE-USE: IT IS VERY WELL FUNCTIONING |  | Re-use of existing notification (button “re-use”) | GR | - | -
59 | using button "RE-USE" all the data are duplicated and we're forced to cancel some sheets such as "passenger list", "imdg cargo list" one by one. It should be better the system automatically cancel some of them | Major | Re-use of existing notification (button “re-use”) | IT | Functionality | Improve update of table rows with full deletion
60 | When searching for ship notifications, only 10 results per page are displayed, without any option to increase this number, thus you have to proceed to the next page to view more results | Major | Search ship notifications | GR | User interface | Improve Layout and UI
61 | in FAL Form5 "Family name, given name" are one field. In our applications are two differents fields which is very inconvenient for uploding . The same remark for "date and place of birth"and ""nature and number of identity document". In FAL form there is no field for visa | Major | Tab Crew and Passengers | RO | Data | -
62 | The ID document when inserting details for crew could also be the seamans book | Minor | Tab Crew and Passengers | GR | Data | -
63 | The format .csv is rather unsual. We prefer .xls | Major | Tab Crew and Passengers | RO | Functionality | Generalise file upload and use XLS
64 | CANNOT UPLOAD ZIP FILES WITH CREW AND PASSENGERS, IT IS CRUCIAL FOR CRUISE VESSELS. | MAJOR | Tab Crew and Passengers | GR | Functionality | Generalise file upload and use XLS
65 | Date of Birth box width needs to be increased |  | Tab Crew and Passengers | MT | User interface | Improve Layout and UI
66 | Possible to be born in the future and Crew or Pax member | Major | Tab Crew and Passengers | NO | User interface | Add data controls in forms
67 | Crew list and Crew effects should be unified in the same file to be uploaded | Minor | Tab Crew and Passengers | IT | Functionality | Propose unified crew & passenger list (for upload, with unified number)
68 | DPG: A LOT OF PACKAGES FOR IMDG CARGO ARE MISSING | Major | Tab DPG | IT | Data | -
69 | On DPG Dangerous and polluting cargo items ''containers'' / it is not possible to indicate the provisions ''LIMITED QUANTITY'' and ''Excepted quantities'' in order to avoid segregation problem as per imdg | Major | Tab DPG | IT | Data | -
70 | On DPG Dangerous and polluting cargo items ''containers'' /it is not possible to indicate when cargo type is MARINE POLLUTANT ''P'' as per imdg | Major | Tab DPG | IT | Data | -
71 | Stowage position for container expeted to be loaded in port of call / it is upsetting the need to update all before the departure | Minor | Tab DPG | IT | ? | -
72 | System does not define between Oil Cargo and container/other cargo |  | Tab DPG | MT | ? | -
73 | Will there be a standard format to follow? |  | Tab DPG | MT | ? | -
74 | Gross Auntities: Metric system suggested (small caps?) |  | Tab DPG | MT | ? | -
75 | It is impossible to insert all DG cargo by container number manually |  | Tab DPG | MT | ? | -
76 | stowage position could provide some suggestions for the position on board (eg. Tank No or bow/row/tier) | Minor | Tab DPG | GR | Data | -
77 | What is the meaning of DPG MANIFEST CONTACT DATAILS ? | Minor | Tab DPG | IT | User interface | Contextual help
78 | If DPG MANIFEST CONTACT DETAILS means who prepared dangerous cargo manifest in the P.O.L. (port of loading), therefore IT MUST BE REPEATED when it changes by P.O.L.; differently please specify the meaning of "DPG Manifest Contact details". | Major | Tab DPG | IT | User interface | Contextual help
79 | textual reference equals to proper technical name? | Minor | Tab DPG | GR | User interface | Contextual help
80 | Missing a button for immidiate duplication of the same data related to different containers /items (often data are the same excepted "position on board" and "Container ID number"). | Major | Tab DPG | IT | User interface | Improve update of table rows with full deletion
81 | BY TYPE-DIGITING THE UN number. THE SYSTEM SHOULD DISPLAY AUTOMATICALLY ALL IMDG INFORMATION; it seems there is no connection with the IMDG code. | Major | Tab DPG | IT | Functionality | DPG database
82 | Missing IMDG catalogue: for experience with other systems, please notice that the insertion of the UN NUMBER automatically retrieves PSN/CLASS/EMS. | Major | Tab DPG | IT | Functionality | DPG database
83 | HOMOLOGATION CODE OF PACKAGES should be provided, according to IMDG Regulations, and the system should automatically provide the kind of packages | Major | Tab DPG | IT | Functionality | DPG database
84 | DPG details should be looked up from a database. The data quality of the reports will be very low when the form accepting whatever you type into it. | Minor | Tab DPG | NO | Functionality | DPG database
85 | Text titles do not fit on screen |  | Tab DPG | MT | User interface | Improve Layout and UI
86 | DPG details form has not enough space for all user input controls. This sould not have been an inline |  | Tab DPG | NO | User interface | Improve Layout and UI
87 | The usage of Locode instead of Location name in the DPG manifest contact details is not practical, especially when there is no Locode for this Location | Major | Tab DPG | GR | Data
88 | IT IS ACTUALLY A BRIDGE OF SECURITY IF A STOWAWAY IS ON BOARD A VESSEL THUS, THE CELL WITH THE 'LOCATION STOWAWAYS JOINED THE SHIP' IT IS HIGHLY RECCOMENDED TO BE INCLUDED ON THE SECURITY PAGE. | MAJOR | Tab Health | GR | Data | -
89 | "Ill persons greater than expected." Can the phrase be improved? |  | Tab Health | MT | User interface | Improve Layout and UI
90 | MISSING SHIP'S DETAINED BEFORE DEPARTURE BY PSC in case vessel is detained by Harbour Master at departure. | Major | Tab Port | IT | Data | -
91 | Some of the vessels proceed Outside Territorial Waters for orders. Next Port of Call is not always known |  | Tab Port | MT | ? | -
92 | Ship is due to expanded inspection: Agent will not know such information |  | Tab Port | MT | ? | -
93 | Voyage - ETD from Last Port: Should read ATD? Time of departure is known |  | Tab Port | MT | Data | -
94 | Purpose of call – Several requirements are known at the last minute or after the vessel is at berth |  | Tab Port | MT | ? | -
95 | Possible to pass to next step without submitting the form. The to actions is a bit confusing. | Minor | Tab Port | NO | ? | -
96 | Validation error on the previous tab (ship) when submitting from the Port tab. | Major | Tab Port | NO | ? | -
97 | Agent name at Port of Call: Suggested Drop-down list |  | Tab Port | MT | ? | -
98 | ATA and ATD can be sent simultaneously for a voyage, or ATD can be sent with ATA field blank, which can be misleading | Major | Tab Port | GR | Functionality | Differentiate Arrival and Departure formalities
99 | What is the meanning of "Position in port of call"? (BERTH ??) | Minor | Tab Port | RO | User interface | Contextual help
100 | What does it mean "Port facility of arrival"? | Minor | Tab Port | RO | User interface | Contextual help
101 | What is meant by Anchored? This is not agent dependant. Berth may not be available and vessel is sent to anchor by VTS |  | Tab Port | MT | User interface | Contextual help
102 | There are no suggestions for the fields "Position in port of call" and "Port facility of arrival" | Major | Tab Port | GR | User interface | Contextual help
103 | A search function for Port of Call field should be useful | Minor | Tab Port | RO | User interface | Add Locode search in fields and display name with locode
104 | There is no search functionality in "Port" textboxes. There should have been som Ajax search functionality. The textbox includes a search icon with no functionality. A user can not remeber all locodes. | Major | Tab Port | NO | User interface | Add Locode search in fields and display name with locode
105 | There is no dropdown list for port of call or previous port | Major | Tab Port | GR | User interface | Add Locode search in fields and display name with locode
106 | Auto completion for the fields: "Last port" and "Port of call" is missing | Minor | Tab Port | BG | User interface | Add Locode search in fields and display name with locode
107 | As reported from the agents the “voyage number” in a port notification can easily change from arrival to departure. Anyway, if I change, in the systema, the “voyage number” in the departure after continuing the arrival, it seems like another arrival notification different from the previous one is created, instead it should be simply a departure notification whose “voyage number” is different from arrival. | Major | Tab Port | IT | Functionality | Remove "voyage number" from UI
108 | The field "Brief description of onboard cargo" might be divided into 3 fields: "Cargo Discharging" ; "Loading" ; "Transit" | Minor | Tab Port | BG | Data | -
109 | Agents should only include the 'Date of Port Call' not the 'Date of Arrival' and 'Date of Departure'. Master may not always cooperate unless the Master has this saved in the onboard computer |  | Tab Security | MT | Data | -
110 | In Malta all ship-to-ship activities are conducted Outside Territorial Waters. Bunker operations/conveyances are not considered as ship-to-ship activities |  | Tab Security | MT | ? | -
111 | To add "Class" in "Issuer type" |  | Tab Security | MT | Data | -
112 | IT COULD BE AN OPPORTUNITY FOR IMPROVEMENT IF A CELL COULD POSSIBLY BE ADDED INDICATING IF THERE IS AMMUNITION ON BOARD A VESSEL | MAJOR | Tab Security | GR | Data | -
113 | SHIP-TO-SHIP ACTIVITIES: if using UNLOCODE* why rqst also Latitude * Longitude * and vice versa? | Minor | Tab Security | IT | User interface | Contextual help
114 | Clarify position details ( form for input datails) | Major | Tab Security | IT | User interface | Contextual help
115 | In the field "Company" one can find only companies created by the Admin. What's happening when the agent has to notify a ship of a new company? | Minor | Tab Ship | RO | User interface | Contextual help
116 | No validation between MMSI, Callsign and flag Country. | Major | Tab Ship | NO | User interface | Add data controls in forms
117 | User can change IMO numer on ship (all ship particulars can be changed of the user) | Major | Tab Ship | NO | Functionality | Reject change of ship IMO number in update notification
118 | ship's store --> quantity --> adding liters and boxes among the measures | Minor | Tab Ship's Stores | IT | Data | -
119 | one more item such as "LITRES" should be added besides KGS and TN | Minor | Tab Ship's Stores | IT | Data | -
120 | Ship stores should accept other quantities than KGM and TN. | Minor | Tab Ship's Stores | NO | Data | -
121 | A SHORT LIST NEEDED TO PICKUP ARTICLES FROM THERE. | MAJOR | Tab Ship's Stores | GR | Data | -
122 | Upload function? |  | Tab Ship's Stores | MT | Functionality | Generalise file upload and use XLS
123 | "Do you confirm that there is sufficient dedicated onboard capacity?" Agent will not be sure |  | Tab Waste | MT | ? | -
124 | A SHORT LIST NEEDED TO PICKUP PORTS FROM THERE. | MAJOR | Tab Waste | GR | ? | -
125 | Drop down list of waste types is too long. Idea would be to propose a first drop down list with groups and a second with sub-groups. Or to arrange a layout of the table per waste groups | Minor | Tab Waste | EMSA | User interface | Improve Layout and UI

## Data (do not modify)
Severity | Functionalities
Minor | *** WEB Request for clearance ***
Major | Overall functionality
Blocking | Search ships
Create a new notification
Search ship notifications
Re-use of existing notification (button “re-use”)
Update an existing notification (button “update”)
Re-use of arrival to create a departure notification (button “continue”)
Tab Ship
Tab Port
Tab DPG
Tab Ship's Stores
Tab Waste
Tab Security
Tab Crew and Passengers
Tab Health
*** Administration of NSW ***
Configure regulatory information
Manage users
Configure access rights
Manage ships
Manage shipping companies
Manage locations
*** XML Request for clearance ***
Overall functionality
Send a new notification
Send an update notification
Receive receipt message from the NSW